## Slide 1
Agreement Revision Task Force
Status report for SPC meeting
March 2, 2021
Jostein Frømyr, Peppol Agreement Coordinator
Trond Ausdal, SP representative in WS A
Paul Simons, SP representative in WS B
Simon Foster, SP representative in WS C

## Slide 2: Presentation outline
Status in the different workstreams
Timeline and way forward
WS A: Agreements
WS B: Operational Procedures
WS C: Internal Regulations
Some high-level observations

## Slide 3: Some high-level observations
We have good and constructive discussions in all workstreams
  where all parties (SP, PA and Operations) are present and being heard
Work in the different workstreams is progressing well
  although not as fast as originally anticipated, but we are picking up speed
Topics are being handled from different viewpoints in the different workstreams (Agreement, IR, OP)
  and we are in the process of aligning content as individual topics are becoming mature enough

## Slide 4: WS A on Agreement Annexes
Status update
Draft Silver versions available for both the PA and SP Agreements
  Bronzer = Agreed table of content
  Silver = Draft text
  Gold = Final text for review and approval
Minimal changes implemented compared to the versions approved by PA vote in July 2020
  Updated references to IR/OP (replacing references to policy documents)
  Added voting rules and minimum time to implement changes to the agreements
    No real changes compared to current TIA annex 6
  Added general requirements related to information security with minimum requirements to be defined in IR/OP
No need for further annexes identified for any of the Agreements
SP representatives participating:
Trond Ausdal
Henrik Möller
Hans Berg

## Slide 5: WS B on Operational Procedures
Status update
Draft Silver version are available for most of the identified topics.
Focused on describing the “How-To”
  depending on different artefacts (e.g. change management might differ between technical and organisational artefacts)
  independent of specific tools to be used
SP representatives participating:
Paul Simons
Trond Ausdal
Anders Ødegård
Currently working on OPs for
  PA Specific Requirements
  Security Requirements
  Onboarding and Accreditation of SP
  Entity Identification and Verification
  Reporting of Statistics
  Issue Reporting and Management
  Non-compliance Management
  Change Management
  Release Management
  Extended Use

## Slide 6: WS C on Internal Regulations
Status update
The IR will be provided in two parts
  Part 1: The organization of the Association
  Part 2: Governance and use of the Peppol Network
    Current status: partially Silver
Current focus is on providing IR Part 2, silver version, related to:
  Entity Identification
  Data Usage and Reporting
  Extended Use
  Change management
Coming next:
  Information Security
  PA Specific Requirements
  Dispute resolution and escalation (Governance)
SP representatives participating:
Simon Foster
Ahti Allikas

## Slide 7: Timeline and the way forward
Timeline
  Work is progressing with an objective to have the final Gold package approved during June, after a 4-week open member review
  Implementation of the new agreements will then be initiated second half of 2021, based on the regulations of the current TIA annex 6 (6-month notice)
Backlog and Issue Register
  Given the focus on MVP, a Backlog and an Issue Register will be established
    The Backlog will identify topics for further work (continuous improvements) within the current governance and organizational framework
    The Issue Register will identify topics that may require changes to the current governance and organizational framework
  A strategy and a plan will be prepared on how to progress with the topics contained in the Backlog and Issue Register